## Task List
Task | Start Date | Duration | End Date
Kick Off | 2015-01-03 | 1 | 2015-01-04
Develop Scoring Matrix | 2015-01-03 | 1 | 2015-01-04
Define Strategy Options | 2015-01-03 | 1 | 2015-01-04
Develop Feature / Attribute Matrix | 2015-01-03 | 1 | 2015-01-04
Define Feature Concepts | 2015-01-04 | 1 | 2015-01-05
Prototype Feature Concepts | 2015-01-05 | 5 | 2015-01-10
Field Element Design and Procurement | 2015-01-04 | 1 | 2015-01-05
Field Element Fabrication and Assembly | 2015-01-06 | 3 | 2015-01-09
Peer Review | 2015-01-05 | 1 | 2015-01-06
Controls Test Rig Fabrication and Assembly | 2015-01-05 | 4 | 2015-01-09
Decision Matrix | 2015-01-10 | 1 | 2015-01-11
Conceptual Design Basis | 2015-01-10 | 1 | 2015-01-11
Preliminary Motor Allocation | 2015-01-12 | 1 | 2015-01-13
Base COTS - Define, Select and Procure | 2015-01-12 | 2 | 2015-01-14
Chassis Fabrication, Layout and Assembly | 2015-01-12 | 5 | 2015-01-17
Acquisition Feature Design | 2015-01-12 | 7 | 2015-01-19
Acquisition Feature BOM | 2015-01-16 | 1 | 2015-01-17
Acquisition Feature Materials Procurement | 2015-01-18 | 1 | 2015-01-19
Acquisition Feature Parts Fabrication | 2015-01-20 | 14 | 2015-02-03
Accumulation Feature Design | 2015-01-12 | 7 | 2015-01-19
Accumulation Feature BOM | 2015-01-16 | 1 | 2015-01-17
Accumulation Feature Materials Procurement | 2015-01-18 | 1 | 2015-01-19
Accumulation Feature Parts Fabrication | 2015-01-20 | 14 | 2015-02-03
Scoring Feature Design | 2015-01-12 | 7 | 2015-01-19
Scoring Feature BOM | 2015-01-16 | 1 | 2015-01-17
Scoring Feature Materials Procurement | 2015-01-18 | 1 | 2015-01-19
Scoring Feature Parts Fabrication | 2015-01-20 | 14 | 2015-02-03
Features COTS - Define, Select and Procure | 2015-01-12 | 2 | 2015-01-14
Controls Design Basis - Autonomous Section | 2015-01-12 | 5 | 2015-01-17
Controls Design Basis - Teleoperated Section | 2015-01-12 | 5 | 2015-01-17
Programming - Base: TeleOp and Autonomous | 2015-01-13 | 4 | 2015-01-17
Programming - Features: TeleOp and Autonomous | 2015-01-13 | 22 | 2015-02-04
Instrumentation - Define, Select and Procure | 2015-01-13 | 2 | 2015-01-15
Driver Station Design and Fabrication | 2015-01-05 | 35 | 2015-02-09
Robot Transportation Cart Design and Fabrication | 2015-01-05 | 35 | 2015-02-09
Bumpers Design and Fabrication | 2015-01-20 | 20 | 2015-02-09
Guarding Design and Fabrication | 2015-01-20 | 20 | 2015-02-09
Branding and Sponsor Logo Design and Fabrication | 2015-01-23 | 24 | 2015-02-16
Machine Assembly | 2015-02-03 | 6 | 2015-02-09
Driving Test of Base - TeleOp, then Autonomous | 2015-01-19 | 5 | 2015-01-24
Machine Testing | 2015-02-09 | 4 | 2015-02-13
Driver Training | 2015-01-10 | 33 | 2015-02-12
Automomous Practice and Enhancement | 2015-02-13 | 4 | 2015-02-17
Drive Team Practice and Enhancement | 2015-02-13 | 4 | 2015-02-17
Branding and Sponsor Logo Application | 2015-02-16 | 1 | 2015-02-17
Stop Build | 2015-02-16 | 1 | 2015-02-17
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]+1
Start Date = [End Date, row above]-3

## Gantt Chart
Key Assumptions:
- KoP Chassis
- Compatible COTS on-hand as needed
- CAD model completed prior to Fabrication
- Two weeks Fabrication