## Sheet1
ID | Task Name |  |  |  |  | Duration | Start | End | Predecessors | Resource Names
1 | Miracle Workerz 2004 |  |  |  |  | 48 days | 2003-12-22 08:00 | 2004-03-03 17:00
2 |  | Drive Train Preliminary Design |  |  |  | 8 days | 2003-12-22 08:00 | 2004-01-15 17:00
3 |  |  | Transfer Drawings to Delaware Metals |  |  | 1 hr | 2003-12-22 08:00 | 2003-12-22 09:00 |  | Drive Train Team
4 |  |  | Supply shaft Drawings to machine shop |  |  | 1 hr | 2003-12-22 09:00 | 2003-12-22 10:00 | 2 | Drive Train Team
5 |  |  | Supply wheel Drawings to machine shop |  |  | 1 hr | 2003-12-22 10:00 | 2003-12-22 11:00 | 3 | Drive Train Team
6 |  |  | Motor Training |  |  | 1 day | 2003-12-29 08:00 | 2003-12-29 17:00 |  | Drive Train Team
7 |  |  | Modify the shaft Drawings |  |  | 3 days | 2004-01-05 08:00 | 2004-01-11 17:00 | 5 | Drive Train Team
8 |  |  | Refine Drive System Design |  |  | 3 days | 2004-01-12 08:00 | 2004-01-15 17:00 | 6 | Drive Train Team
9 |  | Build Game Field |  |  |  | 20 days | 2004-01-10 08:00 | 2004-02-04 17:00
10 |  |  | Buy Materials for 2004 Game Components |  |  | 1 day | 2004-01-10 08:00 | 2004-01-10 17:00 |  | Boosterz
11 |  |  | Buy Materials for 2004 Practice Field |  |  | 1 day | 2004-01-10 08:00 | 2004-01-10 17:00 | 9SS
12 |  |  | Build 2004 Game Components |  |  | 4 days | 2004-01-11 08:00 | 2004-01-15 17:00 | 9 | Boosterz
13 |  |  | Build 2004 Practice Field |  |  | 4 days | 2004-01-11 08:00 | 2004-01-15 17:00 | 10 | Boosterz
14 |  |  | Maintain/Enhance Operator Station |  |  | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 12FS+1 day | Boosterz
15 |  |  | Modify Cart for 2004 Robot |  |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 13FS+1 day | Boosterz
16 |  |  | Modify Shipping Crate for 2004 Robot |  |  | 4 days | 2004-02-01 08:00 | 2004-02-04 17:00 | 14FS+1 day | Boosterz
17 |  | Robot #1 |  |  |  | 40 days | 2004-01-10 08:00 | 2004-02-24 17:00
18 |  |  | Week 1: Strategy & Design |  |  | 5 days | 2004-01-10 08:00 | 2004-01-15 17:00
19 |  |  |  | Understand the Game |  | 1 day | 2004-01-10 08:00 | 2004-01-10 17:00 |  | Full Team
20 |  |  |  | Decide what game components are critical |  | 1 day | 2004-01-10 08:00 | 2004-01-10 17:00 | 18SS | Full Team
21 |  |  |  | 4 Concurrent Divergent Brainstorming Sessions |  | 2 days | 2004-01-10 08:00 | 2004-01-11 17:00 | 18SS | Full Team
22 |  |  |  | List Important Game Strategies |  | 2 days | 2004-01-10 08:00 | 2004-01-11 17:00 | 18SS | Full Team
23 |  |  |  | Monitor Chief Delphi Discussions |  | 4 days | 2004-01-10 08:00 | 2004-01-14 17:00 | 18SS | Full Team
24 |  |  |  | Convergent Brainstorming Session |  | 2 days | 2004-01-11 08:00 | 2004-01-12 17:00 | 19 | Full Team
25 |  |  |  | Select Preliminary Game Strategy |  | 2 days | 2004-01-11 08:00 | 2004-01-12 17:00 | 19 | Full Team
26 |  |  |  | Determine components of concept needed to play the game |  | 1 day | 2004-01-11 08:00 | 2004-01-11 17:00 | 19 | Full Team
27 |  |  |  | Threat team tries to defeat our strategy |  | 3 days | 2004-01-11 08:00 | 2004-01-14 17:00 | 19 | Strategy Team
28 |  |  |  | Discuss Pros & Cons of Design |  | 2 days | 2004-01-12 08:00 | 2004-01-14 17:00 | 25 | Full Team
29 |  |  |  | Select a Robot Type |  | 1 day | 2004-01-12 08:00 | 2004-01-12 17:00 | 25 | Full Team
30 |  |  |  | Figure out Likely Strategys other teams will use |  | 1 day | 2004-01-14 08:00 | 2004-01-14 17:00 | 28 | Full Team
31 |  |  |  | How will our Strategy work with Others' |  | 1 day | 2004-01-14 08:00 | 2004-01-14 17:00 | 28 | Full Team
32 |  |  |  | Analyze Our Weak Points |  | 1 day | 2004-01-14 08:00 | 2004-01-14 17:00 | 28 | Full Team
33 |  |  |  | Select Final Game Strategy |  | 1 day | 2004-01-15 08:00 | 2004-01-15 17:00 | 31 | Full Team
34 |  |  |  | Decide on Robot Concept based on criteria to implement our strategy |  | 1 day | 2004-01-15 08:00 | 2004-01-15 17:00 | 31 | Full Team
35 |  |  |  | Game Strategy Selected & Agreed Upon |  | 0 days | 2004-01-15 17:00 | 2004-01-15 17:00 | 33
36 |  |  |  | Basic Robot Design Selected & Agreed Upon |  | 0 days | 2004-01-15 17:00 | 2004-01-15 17:00 | 33
37 |  |  |  | Assign Team Members to Sub-Teams |  | 1 day | 2004-01-15 08:00 | 2004-01-15 17:00 | 31 | Full Team
38 |  |  |  | Subteams Selected and Working |  | 0 days | 2004-01-15 17:00 | 2004-01-15 17:00 | 36
39 |  |  | Engineering Design Review |  |  | 1 day | 2004-01-16 08:00 | 2004-01-16 17:00 | 17 | Engineers
40 |  |  | Autonomous Programming |  |  | 32 days | 2004-01-18 08:00 | 2004-02-22 17:00 | 38
41 |  |  |  | Prototype Autonomous Drive Program |  | 3 days | 2004-01-18 08:00 | 2004-01-21 17:00 |  | Autonomous Team
42 |  |  |  | Test Autonomous Drive Prototype |  | 1 day | 2004-01-22 08:00 | 2004-01-22 17:00 | 40 | Autonomous Team
43 |  |  |  | Create Autonomous Drive Program |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 41FS+1 day | Autonomous Team
44 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-01 08:00 | 2004-02-01 17:00 | 42FS+1 day | Autonomous Team
45 |  |  |  | Refine Autonomous Drive Program |  | 3 days | 2004-02-02 08:00 | 2004-02-04 17:00 | 43 | Autonomous Team
46 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-05 08:00 | 2004-02-05 17:00 | 44 | Autonomous Team
47 |  |  |  | Finalize Autonomous Drive Program |  | 2 days | 2004-02-07 08:00 | 2004-02-08 17:00 | 45FS+1 day | Autonomous Team
48 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-09 08:00 | 2004-02-09 17:00 | 46 | Autonomous Team
49 |  |  |  | Adjust Autonomous Drive Program |  | 2 days | 2004-02-10 08:00 | 2004-02-11 17:00 | 47 | Autonomous Team
50 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-14 08:00 | 2004-02-14 17:00 | 48FS+2 days | Autonomous Team
51 |  |  |  | Adjust Autonomous Drive Program |  | 2 days | 2004-02-15 08:00 | 2004-02-16 17:00 | 49 | Autonomous Team
52 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-17 08:00 | 2004-02-17 17:00 | 50 | Autonomous Team
53 |  |  |  | Adjust Autonomous Drive Program |  | 1 day | 2004-02-18 08:00 | 2004-02-18 17:00 | 51 | Autonomous Team
54 |  |  |  | Test Autonomous Drive Program |  | 1 day | 2004-02-20 08:00 | 2004-02-20 17:00 | 52FS+1 day | Autonomous Team
55 |  |  |  | Final Adjustments to Autonomous Program |  | 1 day | 2004-02-21 08:00 | 2004-02-21 17:00 | 53 | Autonomous Team
56 |  |  |  | Final Autonomous Drive Installation |  | 1 day | 2004-02-22 08:00 | 2004-02-22 17:00 | 54 | Autonomous Team
57 |  |  | RC Programming |  |  | 32 days | 2004-01-18 08:00 | 2004-02-22 17:00 | 38
58 |  |  |  | Prototype RC Drive Program |  | 3 days | 2004-01-18 08:00 | 2004-01-21 17:00 |  | RC Software Team
59 |  |  |  | Test RC Drive Prototype |  | 1 day | 2004-01-22 08:00 | 2004-01-22 17:00 | 57 | RC Software Team
60 |  |  |  | Create RC Drive Program |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 58FS+1 day | RC Software Team
61 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-01 08:00 | 2004-02-01 17:00 | 59FS+1 day | RC Software Team
62 |  |  |  | Refine RC Drive Program |  | 3 days | 2004-02-02 08:00 | 2004-02-04 17:00 | 60 | RC Software Team
63 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-05 08:00 | 2004-02-05 17:00 | 61 | RC Software Team
64 |  |  |  | Finalize RC Drive Program |  | 2 days | 2004-02-07 08:00 | 2004-02-08 17:00 | 62FS+1 day | RC Software Team
65 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-09 08:00 | 2004-02-09 17:00 | 63 | RC Software Team
66 |  |  |  | Adjust RC Drive Program |  | 2 days | 2004-02-10 08:00 | 2004-02-11 17:00 | 64 | RC Software Team
67 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-14 08:00 | 2004-02-14 17:00 | 65FS+2 days | RC Software Team
68 |  |  |  | Adjust RC Drive Program |  | 2 days | 2004-02-15 08:00 | 2004-02-16 17:00 | 66 | RC Software Team
69 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-17 08:00 | 2004-02-17 17:00 | 67 | RC Software Team
70 |  |  |  | Adjust RC Drive Program |  | 1 day | 2004-02-18 08:00 | 2004-02-18 17:00 | 68 | RC Software Team
71 |  |  |  | Test RC Drive Program |  | 1 day | 2004-02-20 08:00 | 2004-02-20 17:00 | 69FS+1 day | RC Software Team
72 |  |  |  | Final Adjustments to RC Drive Program |  | 1 day | 2004-02-21 08:00 | 2004-02-21 17:00 | 70 | RC Software Team
73 |  |  |  | Install Final RC Drive Program |  | 1 day | 2004-02-22 08:00 | 2004-02-22 17:00 | 71 | RC Software Team
74 |  |  | Week 2: Design and Prototype |  |  | 5 days | 2004-01-18 08:00 | 2004-01-23 17:00
75 |  |  |  | Drive Train Prototype |  | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 38
76 |  |  |  |  | Order Materials for Drive System | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 |  | Drive Train Team
77 |  |  |  |  | Build Prototype Drive System | 2 days | 2004-01-18 08:00 | 2004-01-19 17:00 |  | Drive Train Team
78 |  |  |  |  | Demonstrate proof of concept | 0.5 days | 2004-01-21 08:00 | 2004-01-21 12:00 | 76 | Drive Train Team
79 |  |  |  |  | Final Prototype drive System | 1.5 days | 2004-01-21 13:00 | 2004-01-22 17:00 | 77 | Drive Train Team
80 |  |  |  |  | Select Motors | 1.5 days | 2004-01-21 13:00 | 2004-01-22 17:00 | 77 | Drive Train Team
81 |  |  |  | Mechanical Prototype |  | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 38
82 |  |  |  |  | Wire up Motors for Prototyping | 3 days | 2004-01-18 08:00 | 2004-01-21 17:00 |  | Drive Train Team
83 |  |  |  |  | Prototype game play using Humans | 1 day | 2004-01-18 08:00 | 2004-01-18 17:00 |  | Boosterz
84 |  |  |  |  | Order Preliminary Materials | 1 day | 2004-01-18 08:00 | 2004-01-18 17:00 | 35 | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team
85 |  |  |  |  | Build Early Bolt-together Chassis | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 35 | Chassis Team
86 |  |  |  |  | Build Prototype of Component 1 | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 35 | Mechanical Team 1
87 |  |  |  |  | Build Prototype of Component 2 | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 35 | Mechanical Team 2
88 |  |  |  |  | Build Prototype of Component 3 | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 35 | Mechanical Team 3
89 |  |  |  |  | Build Prototype Electrical Panel | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 35 | Electrical Team
90 |  |  |  |  | Preliminary functional electrical specs due from all teams | 0 days | 2004-01-19 17:00 | 2004-01-19 17:00 | 81SS+2 days
91 |  |  |  | Design Electrical Components |  | 3 days | 2004-01-19 08:00 | 2004-01-22 17:00 | 80SS+1 day
92 |  |  |  |  | Determine Preliminary Electrical Needs | 1 day | 2004-01-19 08:00 | 2004-01-19 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team
93 |  |  |  |  | Prepare Electrical Panel Schematic Drawing | 2 days | 2004-01-19 08:00 | 2004-01-21 17:00 |  | Electrical Team
94 |  |  |  |  | Order needed electrical materials | 1 day | 2004-01-21 08:00 | 2004-01-21 17:00 | 91 | Electrical Team
95 |  |  |  |  | Create prototype electrical board | 2 days | 2004-01-21 08:00 | 2004-01-22 17:00 | 91 | Electrical Team
96 |  |  |  | Prepare Initial Chassis Drawings |  | 4 days | 2004-01-18 08:00 | 2004-01-22 17:00 | 38 | Vince
97 |  |  |  | Engineering Design Review |  | 1 day | 2004-01-23 08:00 | 2004-01-23 17:00 | 74,80,95,90 | Engineers
98 |  |  | Week 3: Build Components |  |  | 5 days | 2004-01-25 08:00 | 2004-01-30 17:00
99 |  |  |  | Evaluate Full Prototype |  | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 | 96
100 |  |  |  |  | Evaluate Feasibility of Prototypes | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
101 |  |  |  |  | Estimate Volume of Components | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
102 |  |  |  |  | Estimate Weight of Components | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
103 |  |  |  |  | Finalize Design | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
104 |  |  |  |  | Determine Final Sub-Team Structural Needs | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
105 |  |  |  |  | Prepare Preliminary Bill of Materials | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
106 |  |  |  | Build Chassis |  | 5 days | 2004-01-25 08:00 | 2004-01-30 17:00 | 96
107 |  |  |  |  | Prepare Final Chassis Drawings | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Vince
108 |  |  |  |  | Final Drawing Due | 1 hr | 2004-01-26 08:00 | 2004-01-26 09:00 | 106 | Vince
109 |  |  |  |  | Deliver Chassis Drawings to machine shop | 1 hr | 2004-01-26 08:00 | 2004-01-26 09:00 | 106 | Vince
110 |  |  |  |  | Build First Chassis | 4 days | 2004-01-26 08:00 | 2004-01-30 17:00 | 106 | Delaware Metals
111 |  |  |  | Build Drive System |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 96
112 |  |  |  |  | Prepare Final Drive System BOM | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 |  | Drive Train Team
113 |  |  |  |  | Order Final Drive System Materials | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 |  | Drive Train Team
114 |  |  |  |  | Final Design drive System | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team
115 |  |  |  |  | Modify Bosch Motors | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 | 79 | Drive Train Team
116 |  |  |  |  | Fabricate First Set of Transmissions | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 114 | Machine Shop
117 |  |  |  |  | Fabricate First Set of Wheels | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 114 | Machine Shop
118 |  |  |  |  | Fabricate parts for First drive system | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 114 | Drive Train Team
119 |  |  |  | Build Mechanical Components |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 96
120 |  |  |  |  | Prepare Final BOM for Mechanical Components | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Electrical Team,Mechanical Team 3,Mechanical Team 1,Drive Train Team
121 |  |  |  |  | Order Materials for Final Mechanical Components | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Electrical Team,Mechanical Team 3,Mechanical Team 1,Drive Train Team
122 |  |  |  |  | Prepare Drawing of Component 1 | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Mechanical Team 1
123 |  |  |  |  | Prepare Drawing of Component 2 | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Mechanical Team 2
124 |  |  |  |  | Prepare Drawing of Component 3 | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Mechanical Team 3
125 |  |  |  |  | Prepare parts for Component 1 | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 121 | Mechanical Team 1
126 |  |  |  |  | Prepare parts for Component 2 | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 122 | Mechanical Team 2
127 |  |  |  |  | Prepare parts for Component 3 | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 123 | Mechanical Team 3
128 |  |  |  | Build Electrical Panel |  | 4 days | 2004-01-25 08:00 | 2004-01-29 17:00 | 96
129 |  |  |  |  | Determine Final Electrical Needs | 1 day | 2004-01-25 08:00 | 2004-01-25 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
130 |  |  |  |  | Prepare Final Electrical Panel Drawing | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 128 | Electrical Team
131 |  |  |  |  | Order needed electrical materials | 3 days | 2004-01-26 08:00 | 2004-01-29 17:00 | 128 | Electrical Team
132 |  |  |  | Engineering Design Review |  | 1 day | 2004-01-30 08:00 | 2004-01-30 17:00 | 110,118 | Engineers
133 |  |  | Week 4: Assembly |  |  | 7 days | 2004-02-01 08:00 | 2004-02-07 17:00
134 |  |  |  | Drive system |  | 5 days | 2004-02-01 08:00 | 2004-02-05 17:00 | 131
135 |  |  |  |  | Assemble First drive System | 4 days | 2004-02-01 08:00 | 2004-02-04 17:00 |  | Drive Train Team
136 |  |  |  |  | Unit test first drive system | 1 day | 2004-02-05 08:00 | 2004-02-05 17:00 | 134 | Drive Train Team
137 |  |  |  |  | First drive system complete | 0 days | 2004-02-05 17:00 | 2004-02-05 17:00 | 135
138 |  |  |  | Mechanical Components |  | 6 days | 2004-02-01 08:00 | 2004-02-06 17:00 | 131
139 |  |  |  |  | Design Robot Graphics | 2 days | 2004-02-01 08:00 | 2004-02-02 17:00 |  | Boosterz
140 |  |  |  |  | Print Robot Graphics | 2 days | 2004-02-03 08:00 | 2004-02-04 17:00 | 138 | Boosterz
141 |  |  |  |  | Build and Paint First Component 1 | 6 days | 2004-02-01 08:00 | 2004-02-06 17:00 |  | Mechanical Team 1
142 |  |  |  |  | Build and Paint First Component 2 | 5 days | 2004-02-01 08:00 | 2004-02-05 17:00 |  | Mechanical Team 2
143 |  |  |  |  | Build and Paint First Component 3 | 4 days | 2004-02-01 08:00 | 2004-02-04 17:00 |  | Mechanical Team 3
144 |  |  |  | Electrical Panel |  | 3 days | 2004-02-01 08:00 | 2004-02-03 17:00 | 131 | Electrical Team
145 |  |  |  | First Robot |  | 7 days | 2004-02-01 08:00 | 2004-02-07 17:00 | 131
146 |  |  |  |  | Paint Chassis | 1 day | 2004-02-01 08:00 | 2004-02-01 17:00 |  | Chassis Team
147 |  |  |  |  | Drive System Assembly | 2 days | 2004-02-02 08:00 | 2004-02-03 17:00 | 145 | Drive Train Team
148 |  |  |  |  | Electrical Assembly | 1 day | 2004-02-04 08:00 | 2004-02-04 17:00 | 146 | Electrical Team
149 |  |  |  |  | Component 3 Assembly | 1 day | 2004-02-05 08:00 | 2004-02-05 17:00 | 147 | Mechanical Team 3
150 |  |  |  |  | Component 2 Assembly | 1 day | 2004-02-06 08:00 | 2004-02-06 17:00 | 148 | Mechanical Team 2
151 |  |  |  |  | Component 1 Assembly | 1 day | 2004-02-07 08:00 | 2004-02-07 17:00 | 149 | Mechanical Team 1
152 |  |  | Week 5: Adjust and Debug |  |  | 6 days | 2004-02-08 08:00 | 2004-02-13 17:00
153 |  |  |  | Adjust and Debug Components |  | 6 days | 2004-02-08 08:00 | 2004-02-13 17:00 | 150
154 |  |  |  |  | Adjust and Debug Component Operation | 6 days | 2004-02-08 08:00 | 2004-02-13 17:00 |  | Drive Train Team,Mechanical Team 1,Mechanical Team 3,Mechanical Team 2
155 |  |  |  |  | Final Electrical Assembly | 1 day | 2004-02-08 08:00 | 2004-02-08 17:00 |  | Electrical Team
156 |  |  |  |  | Load Initial RC & Auto Software | 1 day | 2004-02-09 08:00 | 2004-02-09 17:00 | 154 | Autonomous Team,RC Software Team
157 |  |  |  |  | Debug and Finalize RC & Auto Software | 4 days | 2004-02-10 08:00 | 2004-02-13 17:00 | 155 | Autonomous Team,RC Software Team
158 |  |  |  |  | Preliminary Driver Training | 5 days | 2004-02-09 08:00 | 2004-02-13 17:00 | 154 | Competition Team
159 |  |  |  |  | Completed Robot #1 | 0 days | 2004-02-13 17:00 | 2004-02-13 17:00 | 157
160 |  |  | Week 6: Tuning and Training |  |  | 10 days | 2004-02-14 08:00 | 2004-02-23 17:00
161 |  |  |  | Final Testing and Driver Training |  | 10 days | 2004-02-14 08:00 | 2004-02-23 17:00 | 152
162 |  |  |  | Robot Shipment |  | 1 day | 2004-02-24 08:00 | 2004-02-24 17:00 | 166 | FedEx
163 |  | Robot #2 |  |  |  | 22 days | 2004-02-02 08:00 | 2004-02-23 17:00
164 |  |  | Build Second Robot |  |  | 10 days | 2004-02-02 08:00 | 2004-02-11 17:00 | 109FS+1 day
165 |  |  |  | Build Second Chassis |  | 5 days | 2004-02-02 08:00 | 2004-02-06 17:00 |  | Delaware Metals
166 |  |  |  | Paint Second Chassis |  | 1 day | 2004-02-07 08:00 | 2004-02-07 17:00 | 170 | Drive Train Team
167 |  |  |  | Fabricate Second Set of Transmissions |  | 3 days | 2004-02-06 08:00 | 2004-02-08 17:00 | 133 | Machine Shop
168 |  |  |  | Fabricate Second Set of Wheels |  | 3 days | 2004-02-06 08:00 | 2004-02-08 17:00 | 133 | Machine Shop
169 |  |  |  | Fabricate parts for Second drive system |  | 3 days | 2004-02-06 08:00 | 2004-02-08 17:00 | 133 | Drive Train Team
170 |  |  |  | Build and Paint Second Component 3 |  | 2 days | 2004-02-06 08:00 | 2004-02-07 17:00 | 148 | Mechanical Team 1
171 |  |  |  | Build and Paint Second Component 2 |  | 3 days | 2004-02-07 08:00 | 2004-02-09 17:00 | 149 | Mechanical Team 2
172 |  |  |  | Build and Paint Second Component 1 |  | 4 days | 2004-02-08 08:00 | 2004-02-11 17:00 | 150 | Mechanical Team 3
173 |  |  |  | Build Second Electrical Panel |  | 3 days | 2004-02-09 08:00 | 2004-02-11 17:00 | 154 | Electrical Team
174 |  |  | Assemble Second Robot |  |  | 16 days | 2004-02-08 08:00 | 2004-02-23 17:00
175 |  |  |  | Component 3 Assembly |  | 1 day | 2004-02-08 08:00 | 2004-02-08 17:00 | 175 | Mechanical Team 3
176 |  |  |  | Drive System Assembly |  | 3 days | 2004-02-09 08:00 | 2004-02-11 17:00 | 174,180 | Drive Train Team
177 |  |  |  | Component 2 Assembly |  | 4 days | 2004-02-12 08:00 | 2004-02-15 17:00 | 176,181 | Mechanical Team 2
178 |  |  |  | Electrical Assembly |  | 1 day | 2004-02-16 08:00 | 2004-02-16 17:00 | 178,182 | Electrical Team
179 |  |  |  | Component 1 Assembly |  | 3 days | 2004-02-17 08:00 | 2004-02-19 17:00 | 177,183 | Mechanical Team 1
180 |  |  |  | Final Electrical Assembly |  | 2 days | 2004-02-22 08:00 | 2004-02-23 17:00 | 184FS+2 days | Electrical Team
181 |  |  |  | Load RC & Auto Software |  | 1 day | 2004-02-23 08:00 | 2004-02-23 17:00 | 185SS+1 day | Autonomous Team
182 |  |  |  | Completed Robot #2 |  | 0 days | 2004-02-23 17:00 | 2004-02-23 17:00 | 186
183 |  | Pre-Competition Activities |  |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 | 16,168
184 |  |  | Driver Training |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 |  | Competition Team
185 |  |  | Scouting |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 |  | Scouting Team
186 |  |  | Build/Assemble Spare Parts |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 |  | Drive Train Team,Mechanical Team 3,Mechanical Team 1,Electrical Team,Chassis Team,Mechanical Team 2
187 |  |  | Moe Stix |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 |  | Boosterz
188 |  |  | Mascot |  |  | 5 days | 2004-02-25 08:00 | 2004-03-03 17:00 |  | Boosterz